## Phase map
DocuMind AI: what belongs to which phase
The project folder zip holds the work of Phases 1, 2 and 3 together. The tender module is Phase 2 (design only).
Phase | What it is | Files / work | Status
1 | Requirements and the first backend | backend/ (FastAPI, health checks, 7 tests); docs/DocuMind_AI_Phase1_Requirements_Specification.pdf | Done
2 | System design, including the tender module | docs/phase2/: the 50-page PDF (Chapter 9 = tender module); db/documind_phase2_database.sql (16 tables); api/openapi.yaml (34 operations) | Design done; not yet run on MySQL 8 with the tender tables
3 | Development environment | frontend/ (React + Vite); scripts/check_phase3.py; PHASE3_SETUP.md; backend/requirements-ocr.txt | Files ready; waiting for your check output
4 | Database and backend foundation | Models, migration, login, roles (including COMPANY and APPLICANT), tender tables in code | Not started
5 | Document upload and storage | Upload module; listing and application endpoints; deadline and isolation rules | Not started
Note: the tender code starts in Phase 4 (tables and roles) and Phase 5 (listing and application endpoints). Nothing in the running app uses the tender tables yet.

## Phase 3 steps
Phase 3: what you do now
Legend: yellow cells in the Done column are for you. Choose Yes or No.
Step | What to do | Done
1 | Copy the zip over your project folder. Keep your own backend/.env. | No
2 | In backend: install with .\.venv\Scripts\python.exe -m pip install -r requirements.txt --default-timeout 100 --retries 10 | No
3 | In backend: run .\.venv\Scripts\python.exe ..\scripts\check_phase3.py | No
4 | Send Claude the full output of the check (even if it contains FAIL lines). | No
Steps done |  | 0 of 4
Phase 3 is complete when the checker shows no FAIL lines (SKIP is fine for the OCR libraries).